## IEEE 29148 BRD Checklist
Category | Checklist Item | Description / Question | Status | Notes / Action Items
1. Document & Business Overview | Business Purpose & Drivers | Does the BRD clearly articulate the core business problem, opportunity, or strategic drivers behind the project? | Done | Section 4.3 states the problem (noisy alerts, scarce analysis skills, >1,000 devices), root causes and why now; Section 4.4 lists drivers BO-001 to BO-004. Impact figures are simulated.
| Business Objectives & Success Metrics | Are key performance indicators (KPIs), ROI expectations, and measurable business success criteria explicitly defined? | In Progress | MET-001 to MET-004 have definitions, baselines and targets (Section 4.4). ROI is not defined. Baselines and targets are simulated. Action: re-measure baselines; add ROI or state it is not applicable to a learning project.
| Scope & Boundaries | Are the project in-scope items, explicit out-of-scope items, and operational boundaries unambiguously detailed? | Done | Section 4.5 lists in scope, out of scope, deferred and boundaries. Some detail is simulated.
| Vision Statement | Is there a concise high-level vision statement aligning the project with organizational strategy according to IEEE 29148? | Pending | No vision statement exists. Action: add one to Section 4.2 and link it to the organization/course strategy.
2. Stakeholder & User Analysis | Stakeholder Identification | Are all key internal and external stakeholders, business sponsors, and user classes fully identified and categorized? | Done | Section 4.6 lists STK-001 to STK-003 with interest, influence and adoption blockers; approvers in Section 4.14. STK-002 and STK-003 are simulated.
| User Personas & Profile Characteristics | Are target user profiles, business roles, operational contexts, and domain experience levels adequately specified? | In Progress | NOC engineers are described by role and needs (SN-001 to SN-004). No persona with experience levels or operating context. Action: add a short profile for junior and senior NOC engineers.
| Business Constraints | Are organizational, financial, regulatory, time-to-market, and strategic business constraints documented? | In Progress | CON-001 to CON-003 cover data boundary, simulated data, time and budget (Section 4.9). No regulatory constraint recorded. Action: confirm whether any regulation applies (see item 16).
3. Business Process & Operational Concept | Current State ('As-Is') Workflow | Is the existing business workflow/process documented to provide context for the proposed changes? | Done | Section 4.3 gives a five-step as-is process and a Mermaid diagram. Steps are simulated.
| Target State ('To-Be') Workflow | Is the proposed business process model clearly illustrated, highlighting improvements, automation, or structural changes? | Pending | No to-be process or diagram. Action: add a to-be flow to Section 4.3 showing alert grouping, cause suggestion and automatic report.
| Operational Scenario & Use Cases | Are high-level business scenarios and primary business use cases described from the end-user/business perspective? | Pending | No business scenarios or use cases. Action: add 3 to 4 scenarios, e.g. alert storm from one failure, junior engineer handling a routing flap, report after closure.
4. Business & High-Level Functional Requirements | Singularity & Clarity | Is each business requirement written as a single, unambiguous statement using standardized IEEE wording (e.g., 'The system shall...')? | Done | BR-001 to BR-011 use the "shall" form with one obligation each (Section 4.7).
| Completeness & Implementation-Free | Are business requirements complete and stated purely in terms of business capabilities rather than technical design/implementation details? | Done | Requirements are stated as business outcomes; no technology named. BR-010 refers to CON-001, which is a constraint, not a design.
| Traceability & Rationale | Does each requirement include a clear business justification/rationale and a unique identifier for downstream requirements tracing? | Done | Each requirement has an ID, rationale and source (BO/SN/CON); Section 4.11 gives the traceability matrix. Downstream PRD IDs are still TBD.
| Feasibility & Realism | Are all business requirements achievable within the known business context, operational constraints, and technology capability? | In Progress | Targets fit the 16-week, USD 500 simulated envelope on paper (CON-003), but feasibility was not analysed and the local-only boundary (RSK-002) may limit capability. Action: assess feasibility during PRD/SAD.
5. Business Quality & Non-Functional Attributes | Compliance & Regulatory Standards | Are legal, regulatory, compliance, data privacy (e.g., GDPR, HIPAA), and auditability requirements fully identified? | Pending | Only the internal data-boundary constraint (CON-001) is recorded. No privacy or audit requirement. Action: state which regulations apply, or that none do, and add an auditability requirement if needed.
| Business Continuity & Availability | Are business impact expectations for system downtime, recovery time objectives (RTO), and availability targets defined? | Pending | No availability, downtime or recovery expectation. Action: state what happens to NOC work if the assistance is unavailable, and set an availability or recovery target, or record it as out of scope.
| Security & Business Policy Constraints | Are high-level security, access control guidelines, and business policy enforcement rules established? | In Progress | CON-001, BR-010 and BRU-001 to BRU-003 cover data handling and incident rules. No access-control or user-permission policy. Action: add who may see incident data and approve actions.
6. Assumptions, Dependencies & Risks | Business Assumptions | Are all critical underlying business assumptions, facts, and expectations explicitly stated? | Done | ASM-001 and ASM-002 with impact, owner and due date (Section 4.10).
| Dependencies & Constraints | Are interdependencies with other business initiatives, third-party services, legacy systems, or vendor deliveries mapped? | Done | DEP-001 (dataset) and ASM-002 (existing monitoring system) with owners and dates. No third-party or vendor dependency is stated.
| Business Risks & Mitigation | Are major business risks identified along with potential mitigation strategies and contingency plans? | Done | RSK-001 to RSK-003 with severity, owner and mitigation (Section 4.10). No contingency plan is given for RSK-002.